## Tasks
Minimum List of Group Project Task |  | EEET2580 Teamwork Contribution Document
You should add more based on your group's work |  | SQUAD Son Tinh - GROUP Job Applicant
Design ERD |  | Name: Dinh Xuan Minh |  |  | Name: Nguyễn Việt Quân |  |  | Name: Huynh Ngoc Duy |  |  | Name: Huynh Nhat Anh |  |  | Name: Tran Minh Truong
Refine ERD |  | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed
MILESTONE 1
Review ERD | ERD Design | Design ERD | Nov 10, 2025 | Nov 10, 2025 | Refine ERD | Nov 10, 2025 | Nov 10, 2025 | Design ERD | Nov 10, 2025 | Nov 10, 2025
|  | Refine ERD | Nov 10, 2025 | Nov 17, 2025 | Review ERD | Nov 10, 2025 | Nov 17, 2025 | Refine ERD | Nov 10, 2025 | Nov 17, 2025
Design System Architecture for Level X Requirement RXY |  | Review ERD | Nov 10, 2025 | Nov 17, 2025 |  |  |  | Review ERD | Nov 10, 2025 | Nov 17, 2025 | Review ERD | Nov 17, 2025 | Nov 17, 2025 | Review ERD | Nov 17, 2025 | Nov 17, 2025
Refine System Architecture for Level X Requirement RXY | Architecture Design | Design System Architecture for Level 2 Back-end | Nov 10, 2025 | Nov 10, 2025 | Design System Architecture for Level 1 |  |  | Design System Architecture for Level 2 Back-end | Nov 10, 2025 | Nov 26, 2025 | Design System Architecture for Level 2 Front-end | Nov 20, 2025 | Nov 21, 2025 | Design System Architecture for Level 2 Front-end | Nov 20, 2025 | Nov 21, 2025
Review System Architecture for Level X Requirement RXY |  | Refine System Architecture for Level 2 Back-end | Nov 15, 2025 | Nov 15, 2025 | Refine System Architecture for Level 2 Back-end | Nov 10, 2025 | Nov 10, 2025 | Refine System Architecture for Level 2 Back-end | Nov 15, 2025 | Nov 26, 2025 | Refine System Architecture for Level 2 Front-end | Nov 25, 2025 | Nov 25, 2025 | Refine System Architecture for Level 2 Front-end | Nov 25, 2025 | Nov 25, 2025
|  | Review System Architecture for Level 2 Back-end | Nov 15, 2025 | Nov 15, 2025 | Review System Architecture for Level 2 Back-end | Nov 20, 2025 | Nov 23, 2025 | Review System Architecture for Level 2 Back-end | Nov 15, 2025 | Nov 28, 2025 | Review System Architecture for Level 2 Front-end | Nov 27, 2025 | Nov 27, 2025 | Review System Architecture for Level 2 Front-end | Nov 27, 2025 | Nov 27, 2025
Design UX/UI for Level X Requirement RXY |  | Design System Architecture for Level 3 Back-end Component notification, Profile Management | Nov 16, 2025 | Nov 19, 2025 | Design System Architecture for Level 3 Back-end Component Application, File Storage, Subscription | Nov 15, 2025 | Nov 15, 2025 | Design System Architecture for Level 3 Back-end Component: Auth, Job Search, Search Profile | Nov 27, 2025 | Nov 28, 2025 | Design System Architecture for Level 3 Front-end Component: Admin, Profile | Nov 22, 2025 | Nov 22, 2025 | Design System Architecture for Level 3 Front-end Component: Auth, Application, Jobsearch, Subscription | Nov 22, 2025 | Nov 22, 2025
Refine UX/UI for Level X Requirement RXY |  | Refine System Architecture for Level 3 Back-end All Components | Nov 20, 2025 | Nov 23, 2025 | Refine System Architecture for Level 3 Back-end All Components | Nov 16, 2025 | Nov 16, 2025 | Refine System Architecture for Level 3 Back-end All Components | Nov 27, 2025 | Nov 28, 2025 | Refine System Architecture for Level 3 Front-end all components | Nov 25, 2025 | Nov 25, 2025 | Refine System Architecture for Level 3 Front-end all components | Nov 25, 2025 | Nov 25, 2025
Review UX/UI for Level X Requirement RXY |  | Review System Architecture for Level 3 Back-end All Components | Nov 20, 2025 | Nov 23, 2025 | Review System Architecture for Level 3 Back-end All Components | Nov 21, 2025 | Nov 23, 2025 | Review System Architecture for Level 3 Back-end All Components | Nov 27, 2025 | Nov 28, 2025 | Review System Architecture for Level 3 Front-end all components | Nov 28, 2025 | Nov 28, 2025 | Review System Architecture for Level 3 Front-end all components | Nov 28, 2025 | Nov 28, 2025
|  | Review System Architecture for Level 2 Front-end Container Diagram | Nov 25, 2025 | Nov 26, 2025 | Design System Architecture for Level 2 Front-end | Nov 15, 2025 | Nov 23, 2025 | Review System Architecture for Level 2 Front-end Container Diagram | Nov 27, 2025 | Nov 28, 2025 | Document [R02] [C4/FE Container Diagram] | Nov 28, 2025 | Nov 28, 2025 | Document [R02] [FE/Frontend Architecture Justification] | Nov 28, 2025 | Nov 28, 2025
HTML/CSS for Level X Requirement RXY |  | Review System Architecture for Level 3 Front-end All Components | Nov 25, 2025 | Nov 26, 2025 | Refine System Architecture for Level 2 Front-end | Nov 21, 2025 | Nov 25, 2025 | Review System Architecture for Level 3 Front-end All Components | Nov 27, 2025 | Nov 28, 2025 | Document [R02] [C4/Describe FE Component Diagram] | Nov 28, 2025 | Nov 28, 2025 | Document [R02] [C4/Describe FE Component Diagram] | Nov 28, 2025 | Nov 28, 2025
|  | Document [R01] [ERD /Introduction] | Nov 25, 2025 | Nov 26, 2025 | Document [R02] [C4/Job Applicant Container] | Nov 28, 2025 | Nov 28, 2025 | Document [R01] [ERD/Justification] | Nov 28, 2025 | Nov 28, 2025
|  | Document [R02] [C4/Job Manager Container] | Nov 28, 2025 | Nov 28, 2025 | Document [Conclusion] | Nov 28, 2025 | Nov 28, 2025 | Document [R01] [ERD/Shard key] | Nov 28, 2025 | Nov 28, 2025
|  | Document [R02] [BE/Justification] | Nov 28, 2025 | Nov 28, 2025
|  | Document [R02] [C4/Describe Component Diagram] | Nov 28, 2025 | Nov 28, 2025
MILESTONE 2
SQL Queries for Level X Requirement RXY | UX / UI Design
Back-end Implementation for Level X Requirement RXY
Document [R0X] [Diagram/Justification]
Refine [R0X] [Diagram/Justification]
Review [R0X] [Diagram/Justification] | Front-end Development
Task of your own choice
Back-end Development
Reporting